## Roles and Responsabilities
#​ |  | Role​ | Name​ | Organization ​ | Responsibility ​
1 | 1 ​ | Supplier ​ | Accenture (Jauk Bierema) ​ | ACN / OB / OTHER​ | Create and send draft, adjust, countersign​
Orange Business (Joanna Morawiec)​
Other Suppliers (Sales Representative)​
2 | 2​ | Lead Architect ​ | Efrayim Metin ​ | MUSIC3 Core Team​ | Review Network Infra related content​
3 | 3. ​ | Project Manager* ​ | Raymond Gerritsen (Accenture, GSS, until roll-out)​ | MUSIC3 Core Team​ | Review agreement (non-Network Infra related content)​
William Jan de Koning (OB, until roll-out)​
Joris Vermeer (various) ​
Jan Oomen (Infinity, various)​
4 | . ​ | PMO​ | Freya Swart​ | MUSIC3 Core Team​ | Review, Track status, Process & Storage ​
5 | 5. ​ | MUSIC3 Procurement​ | Raymond van Amerom​ (backup Quang Tran) | MUSIC3 Core Team​ | Review Commercial T&C’s​
6 | 6. ​ | Program Manager​ | William Mol​ | MUSIC3 Core Team​ | Final review, send when ready for approval​
7 | 7. ​ | Global Tech. Director Infra & Platforms​ | Carolyn Tapang​ | JDE​ | Approval by email ​
8 | 8. ​ | Vendor Management ​ | Stefan Dijs / Mathilde Post​ | JDE​ | Check requirements before signing, send for sign-off, share signed OF with supplier, store countersigned version in Ariba ​
9 ​ |  | CIO​ | Alexander Min ​ | JDE​ | Sign-off in DocuSign ​

## Dashboard Contracting Vendors
MULTI VENDOR DASHBOARD - STATUS CONTRACTING MUSIC3 (TRACKER UNTIL FINAL REVIEW)
REVIEWERS (Date when approved)
Order / quote ID | Contract sub ID | Vendor name | Contracting Owner | PM lead | Phase/ project | SoW/Order description | Comments | Prio | SoW status | Efrayim | Raymond G | Willem Jan de Koning | Raymond van A | Joris Vermeer (run only) | Jan Oomen | Regien Schagen | William Mol | PM | PM Contr. | JDE SME's - contracting
11788446 | 001 | Accenture | Ray | Regien | Design | Business Transformation resources | Helen & Ruben | 1 | 5. Signed | [8 empty] | Raymond G | Joris
11788462 | 002 | Accenture | Ray | Raymond G. | Design | OT Central DMZ - basis Azure infrastructure Accenture | Azure Tenant, Azure Backup, DNS, NTP, SMTP, Azure AD, Reporting, Management, Monitoring + review Local OT ISO Zone (Azure HCI Stack), + review Decentral Access Mgt - local AD | 1 | 5. Signed | [8 empty] | Raymond G | Joris | Efrayim, Farhan, Bogdan, Marcel, Peter
11788467 | 003 | Accenture | Ray | Raymond G. | Design | Secure Managed File Transfer | Selected tool is VShell | 1 | 5. Signed | [8 empty] | Raymond G | Joris | not in scope MUSIC3 contracting - only TOM
11788474 | 004 | Accenture | Ray | Raymond G. | Design | OT RAS Solution | JDE to deliver RACI + ACN to provide input | 2 | 0. Expected | [8 empty] | Raymond G | Joris | Efrayim, Farhan, Bogdan, Joost, OT MU SME’s
11788488 | 005 | Accenture | Ray | Raymond G. | Design | Local Backup & Restore |  | 2 | 5. Signed | [8 empty] | Raymond G | Joris | Efrayim, Farhan, Bogdan, Marcel, OT MU SME’s
11788505 | 006 | Accenture | Ray | Raymond G. | Design | Patching Support Svcs - incl. WSUS, LINUX, AV, EDR, |  | 1 | 5. Signed | [8 empty] | Raymond G | Joris | Efrayim, Farhan, Bogdan, Joost, OT MU SME’s
11788511 | 007 | Accenture | Ray | Regien | Design | AV - Anti Virus / EDR | tool selection required | 3 | 0. Expected | [8 empty] | Raymond G | Joris | Efrayim, Bogdan, Peter/Rachel, OT MU SME’s
0011792226 (TBC) | 010 | Accenture | Ray | Regien | Design | Claroty SOC/SIEM Design + Build integration | request Marcel |  | 0. Expected
11795296 | 011 | Accenture | Ray | William | Design | Backfill EUS IT/OT (Hussam) | request Oscar |  | 5. Signed
SOW205 | WO100 | Accenture | Ray | Raymond G. | Build | OT Central & local Build | All services except EDR | 1 | 2. Under review MUSIC3 | tbd | tbd |  | 26.06.23 |  |  |  | tbd
| 003 | Orange Business | Ray | Willem Jan | Build |  |  |  | 5. Signed | 2023-05-19 |  | 2023-05-19 | 2023-05-24 |  |  |  | 2023-05-24
| 005 | Orange Business | Ray | Willem Jan | Generic | SOW 005 - Orange Business - Demand Coordinator |  |  | 5. Signed |  |  | 2023-05-09 | 2023-05-09 |  |  |  | 2023-05-24
ID0038897-5 | n/a | Accenture | n/a | Jan | Claroty | Claroty licenses (4 sites; Berlin / Kingsgrove / Bremen / Banbury Oxford) - 12 months |  |  | 5. Signed | [5 empty] | 2023-05-19 |  | 2023-05-19
6578 | n/a | GSS | n/a | Willem Jan | Site roll-out | C9500-48Y4C-A incl. accessoires | Comments Efrayim: Is de missende dist switch ( die naar uk is geswitchverstuurd). GSS did send update with right delivery address. GSS wacht op PO nummer, staat al klaar voor verzenden. Wacht op PO |  | 5. Signed | 2023-04-20 |  | 2023-05-30 |  |  |  |  | 2023-06-02
|  | Accenture | Ray |  | Build | AV - Anti Virus / EDR |  |  | 0. Expected
|  | GSS | Quang |  | RUN | GSS - HW delivery contract |  |  | 0. Expected
|  | GSS | Quang |  | Build | GSS - HW delivery SoW's - multiple |  |  | 0. Expected
| 004 | Orange Business | Quang | Willem Jan | Build | SOW 004 - Orange Business - Central Build - MNSS | Sent by Joanna 12/6 |  | 5. Signed | 2023-06-14 |  | 2023-06-14 | 2023-06-15 |  |  |  | 2023-06-16
| 006 | Orange Business | Quang | Willem Jan | Build | SOW 006 - Orange Business - Site by site - Utrecht |  |  | 2. Under review MUSIC3 | 2023-07-10 |  | 2023-07-10 | 2023-07-17 |  | 2023-07-10
|  | Orange Business | Quang |  | Build | X |  |  | 0. Expected
|  | Accenture | Ray |  | RUN | OT RUN Support Contract |  |  | 0. Expected
|  | Accenture | Ray |  | RUN | OT Security RUN Support Contract - amendment |  |  | 0. Expected
|  | Beyond Trust | Ray |  | Licenses | OT RAS Contract licenses + Implementation Beyond Trust |  |  | 0. Expected
|  | TBD | Quang |  | Licenses | EDR License Contract |  |  | 0. Expected
|  | TBD | Quang |  | Licenses | MSFT License Contract |  |  | 0. Expected
SOW205 | WO014 | Accenture | Ray | Raymond G. | Overall | Demand Coordinator Jauk Bierema | Expected 16.06, received 26.06 |  | 2. Under review MUSIC3 |  | 27.06.23 |  | 26.06.23 (Quang) |  |  |  | tbd
|  | Accenture | Ray |  | Design/Build | Lead Architect Adrian Beyers | Expected 16/6 |  | 0. Expected
Remark:
After final approval (Carolyn Tapang) the contract will be added to the Financial Tracker for budget purposes

## Sheet2
Scope : MUSIC3 Central program orders for Design / Build / Transformation / others
Contract approval flow:
1.Supplier sends email with draft order to:
a)Network Infra related à Lead Architect + Project Manager + Program Manager + MUSIC3 Procurement, Cc PMO
b)Non-Network Infra related à Project Manager + Program Manager + MUSIC3 Procurement, Cc PMO
2.MUSIC3 Core Team sends feedback/approval to PMO + date approved in tracker, Cc to all (#1-6 R&R)
3.After review and approval from Core Team, William will do the final review and start the approval process with Carolyn Cc PMO and GIS Vendor Management to validate requirements before sign-off
4.This MUSIC3 approved version will be stored on the MUSIC3 SharePoint under Program Management by PMO
5.After Carolyn’s approval, Vendor Management will place the order in the batch for sign-off CIO (Tuesday afternoon = signing day!)
6.GIS Vendor Management shares the signed version (PO# if known) to Supplier CC to Program Manager and PMO
7.Supplier will countersign and share with Vendor Management cc PMO

## Central Build Planning (hidden)
|  | Week# |  |  | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46 | Week 47 | Week 48 | Week 49 | Week 50 | Week 51 | Week 52 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Start date | time axis 2023-03-06 to 2024-03-18
ID | Design contracts | ACN Delivery Owner | OT SME | RUN SPOC
002 | OT Central DMZ - basis Azure infrastructure Accenture | Adrian + Erwin |  | GP + Srini + Jeevan
003 | Secure Managed File Transfer | Dana Akary
004 | OT RAS Solution | Krzystof (TBC)
005 | Local Backup & Restore | Adrian + Jeroen
006 | Patching Support Svcs - incl. WSUS, LINUX | Adrian + Erwin
007 | AV - Anti Virus / EDR | TBD
N/A | Local OT ISO Zone - Local S2D stack | Dana
N/A | Decentral Access Mgt - Local AD | Arjen + Dana + Offshore
N/A | Decentral Access Mgt - PKI | TBD
N/A | Decentral Access Mgt - IAM | TBD
010 | Claroty SOC/SIEM Design + Build integration | TBD
011 | Backfill EUS IT/OT (Hussam) | Hussam
ID | Build & Transition contracts | ACN Delivery Owner
100 | OT Central Build EMEA | TBD
101 | Site 1 BUILD + TRANSITION (Utrecht) | TBD
102 | Site 2 BUILD + TRANSITION | TBD
103 | Site 3 BUILD + TRANSITION | TBD
104 | Site 4 BUILD + TRANSITION | TBD
105 | Site 5 BUILD + TRANSITION | TBD
106 | Site 6 BUILD + TRANSITION | TBD
107 | Site 7 BUILD + TRANSITION | TBD
108 | Site 8 BUILD + TRANSITION | TBD
109 | Site 9 BUILD + TRANSITION | TBD
110 | Site 10 BUILD + TRANSITION | TBD
111 | Site 11 BUILD + TRANSITION | TBD
112 | Site 12 BUILD + TRANSITION | TBD
113 | Site 13 BUILD + TRANSITION | TBD
114 | Site 14 BUILD + TRANSITION | TBD
115 | Site 15 BUILD + TRANSITION | TBD
116 | Site 16 BUILD + TRANSITION | TBD
117 | Site 17 BUILD + TRANSITION | TBD
118 | Site 18 BUILD + TRANSITION | TBD
119 | Site 19 BUILD + TRANSITION | TBD
120 | Site 20 BUILD + TRANSITION | TBD
121 | Site 21 BUILD + TRANSITION | TBD
122 | Site 22 BUILD + TRANSITION | TBD
ID | Run contracts | ACN Delivery Owner
200 | OT Run | Hidde + (Delivery)
Legend
Completed
In Progress
Issue
Not started
Deadline
Requirements
Delivery
Requirements
Requirements
Requirements
SoW Sign.
SoW Creation
SOW Signed
Delivery
Acceptance
SOW Creation
SOW Signed
Delivery
Acceptance
SOW Creation
SOW Signed
Delivery
Acceptance
Requirements
SOW Creation
SOW Signed
Delivery
Acceptance
Requirements
SoW Creation
Acceptance
SOW Signed
Requirements
SOW Creation
SOW Signed
Delivery
Acceptance
SOW Creation
SOW Signed
Delivery
Acceptance
Design creation (by JDE)
Design creation (by JDE)
Design creation (by JDE)
Review
Acceptance
Review
Acceptance
Review
Acceptance
Today
Design creation (by JDE)
Review
Acceptance
Commitment
Commitment
Commitment
Requirements
SoW Creation
SOW Signed
Delivery
Acceptance
Requirements
SOW Creation
SOW Signed
Delivery
Acceptance
Deadline
Requirements
SoW Creation
SOW Signed
Service Setup
Service Readiness Test
OT Run
HOTO - Site 1
HOTO - Central B
Delivery
SOW Signed
Preparation

## List
0. Expected
1. Sent by Vendor
2. Under review MUSIC3
3. Reviewed by MUSIC3
3. Sent for Approval
4. Send for Signature
5. Signed
Not Applicable